## Stuff Done
Stuff Done | Details
Selection Box | (Ground + Air Units)
little mushroom guy
Login backend | (Create and login to accounts through game client)
(SQL Server to store data)
ART
Sample Plant Harvester | Rigging: Done (Possible Redo) | Animation: Not Done | Mushroom/Acorn sled foot guy
Sample Machine Flying Unit | Rigging: Done | Animation: Not Done | 3 Tentacle Laser shooty guy
Sample Machine Harvester | Rigging: Done | Animation: Not Done | Lil robot dude? (or is just test model)
Sample Machine Tier 1 Unit | Rigging: Done | Animation: Not Done | Tank unit?

## Stuff to Do
Stuff To Do | Details
ART
Sample Plant Tier 1 Unit | ?
Sample Plant Tier 2 Unit | ?
Sample Plant Flying Unit | ? Maple Tree Seedling ? | On death, twirls to the ground, creating a seedling of itself. If the seedling survives X seconds, a new Sample Plant Flying unit is created. This unit cannot reproduce.
Sample Plant Building | ?
Sample Machine Tier 2 Unit | ?
Sample Machine Building | ?
Resource Nodes (?)
Sound Assets
Background music
Sound effects for interacting with the UI
PROGRAMMING
Pathfinding
Unit movement
Unit movement across server
Faction Territory Spread (ie. plants spread forest, machines spread concrete)
Building 'creation' | Click UI element, spawn ghost building at cursor, send Build Action to unit on player commit
Game UI
Combat | Units automatically attack enemies if within a certain distance + Units prioritize enemy units in range
AI
Update service | Allow clients to easily update their game, without downloading the whole enitre game again
DOCUMENTATION OF CODE
INTEGRATION
Integrate Sample Plant Harvester
Integrate Sample Plant Tier 1 Unit
Integrate Sample Plant Tier 2 Unit
Integrate Sample Plant Flying Unit
Integrate Sample Plant Building (Only building (?))
Integrate Sample Machine Harvester
Integrate Sample Machine Tier 1 Unit
Integrate Sample Machine Tier 2 Unit
Integrate Sample Machine Flying Unit
Integrate Sample Machine Building
Pathfinding
Generate grid of nodes
Use A* to search for path to target
Distribute search over multiple frames
Can approximate
Group units with similar/same move command into a super group

## BrainstormingIdeas
Resources
Physically harvest the resources (using workers ala SCVS/Probes)
Passively harvest resources from tiles (ala Civilization)
Faction Feeling
Plants |  | Machines
Less direct
Reproduce (? Certain units) |  | Mass produced
Slower but more powerful |  | Faster
Units build units |  | Units build buildings build units
Grow units on your territory |  | Like Terran (from StarCraft 2)
Resources are spent, seed is placed, and then has to grow
Less agressive
Chaos Plants - Weeds (grow very fast, very annoying)
Balance Plants - Trees (grow slowly, very strong)
Chaos/Balance is Tier 2 +
Neutral is Tier 1
Tree of Life is only building
Units are researched here (after research is complete, several of the researched unit are spawned)
Tree of Life constantly spreads forest (1 unit/second ?)
Resources
Each tile gives X basic resources every Y seconds
Mid-advanced resources must be collected from a resource hotspot location
Maybe plants collect these resources slower, but never mine them out (infinite resources, but slower)
Very advanced/high tech resource - collected in a very hard way
Possibly only spawns in the middle of the map?
Covering 80% of the map with your territory is a victory condition, as well as destroying all the opponents buildings
Choosing a Subfaction - Balance vs Chaos

## Units
| Forests | Machines
Combat
Basic Combat Unit
Construction
Scavenging
Support/Spells